## Encuesta (hidden)
Temática | Pregunta
Aspectos éticos y profesionales | Dispongo de suficiente libertad para orientar la investigación que realizo en la universidad
Aspectos éticos y profesionales | La investigación que realizo tiene un impacto relevante y considero que beneficia a la sociedad
Aspectos éticos y profesionales | La temáticas de la investigación que realizo está determinada por la financiación que obtengo en base a convocatorias públicas o contratos con empresa
Aspectos éticos y profesionales | Considero que existe una imposición de temas de investigación por los equipos directivos de las estructuras de investigación (Institutos, Departamentos, etc.)
Aspectos éticos y profesionales | Conozco que existen una serie de un comités de ética en la universidad y sus funciones
Aspectos éticos y profesionales | Tengo clara la propiedad intelectual de los resultados de la investigación que realizo como empleado de la UPV
Aspectos éticos y profesionales | Conozco la responsabilidad que tengo a la hora de realizar mi trabajo como investigador
Aspectos éticos y profesionales | Existe un alto grado de burocratización de la actividad investigadora en la UPV
Aspectos éticos y profesionales | Considero que la universidad dispone de suficiente información de la evolución de cada uno de los proyectos de investigación en curso
Aspectos éticos y profesionales | Considero que dispongo de los conocimientos necesarios para realizar una correcta gestión de un proyecto de I+D, desde la planificación hasta la ejecución pasando por la organización de recursos y el seguimiento del mismo.
Aspectos éticos y profesionales | Conozco el marco regulatorio de las actividades de I+D
Aspectos éticos y profesionales | Soy consciente de cuáles son las obligaciones contractuales de un investigador predoctoral
Aspectos éticos y profesionales | La actividad docente de los investigadores predoctorales se ajusta bien a las necesidades docentes marcadas por el centro y el departamento
Aspectos éticos y profesionales | El contrato predoctoral me permite acumular la experiencia docente necesaria para progresar en mi carrera como investigador
Aspectos éticos y profesionales | La universidad ha establecido numerosos mecanismos de control a la actividad de I+D que le hace perder competitividad
Aspectos éticos y profesionales | La UPV me proporciona los recursos TIC necesarios para almacenar de manera segura la información y documentación que voy generando de mi actividad de I+D
Aspectos éticos y profesionales | En la universidad tengo el soporte necesario respecto a la aplicación de la legislación de protección y explotación de resultados de investigación
Aspectos éticos y profesionales | La explotación de resultados está suficientemente valorada en el curriculum de los investigadores
Aspectos éticos y profesionales | La universidad dispone de los recursos materiales, humanos y económicos para hacer una comercialización efectiva de los resultados de I+D
Aspectos éticos y profesionales | Los investigadores de todos los niveles tienen la posibilidad de comercializar los resultados de su actividad de I+D
Aspectos éticos y profesionales | Me interesa que mi actividad investigadora y la de la universidad en su conjunto llegue a la sociedad de una manera entendible
Aspectos éticos y profesionales | Estoy contento con la política e conciliación de mi actividad laboral como investigador y mi vida personal
Aspectos éticos y profesionales | En la actividad investigadora no se discrimina en función de sexo, raza o religión
Aspectos éticos y profesionales | Considero que el IAI representa de manera adecuada mi actividad como investigador en la UPV
Contratación y selección | Deben definirse stándares para la admisión de investigadores con cargo a proyectos de investigación con una serie de funciones comunes
Contratación y selección | Considero que es adecuado el sistema de selección de personas con cargo a proyectos de investigación
Contratación y selección | En mi puesto de trabajo como investigador tengo unas perspectivas de desarrollo profesional claramente definidas
Contratación y selección | Las figuras existentes en la LOU y en la Ley de la Ciencia son adecuadas para cubrir la actividad investigadora de la universidad
Contratación y selección | La composición de los comités de selección es adecuada en cuanto al nivel de los miembros y las áreas que abarcan
Contratación y selección | Creo que sería conveniente incorporar en los comités de selección personas provenientes del sector privado y vinculadas con la actividad de I+D
Contratación y selección | Considero que la publicidad que se hace de las ofertas laborales en investigación de la UPV es adecuada
Contratación y selección | Considero que hay suficiente transparencia en las condiciones de contratación de personal que realiza funciones de investigación son
Contratación y selección | Creo que la información que me proporciona la ANECA en los procesos de acreditación es suficiente para identificar los puntos fuertes y áreas de mejora de mi curriculum
Contratación y selección | Debería implementarse un sistema de valoración de méritos de carácter cualitativo complementario al cuantitativo que se aplica en la actualidad
Contratación y selección | La experiencia profesional y la movilidad se valora de manera adecuada en los baremos utilizados en los procesos de selección
Contratación y selección | La universidad proporciona mecanismos adecuados para reincorporarse a la universidad tras estar contratado en una empresa
Contratación y selección | Creo que la movilidad está adecuadamente reconocida en todas las figuras contractuales de la UPV
Contratación y selección | El reconocimiento de méritos y titulaciones de investigadores extranjeros es eficaz
Contratación y selección | La experiencia "no formal" debería reconocerse de manera adecuada en los procesos de selección
Contratación y selección | Conozco la normativa de contratación y selección que se aplica en la UPV
Contratación y selección | Considero que en la UPV se dan las circusntancias adecuadas para desarrrollar mi carrera como investigador
Contratación y selección | Las opciones que tengo de desarrollar mi carrera investigadora en la universidad son homogéneas independientemente de la estructura de investigación en la que me encuentre
Contratación y selección | Existe un marco jurídico adecuado para el desarrollo de la actividad investigadora en la universidad
Contratación y selección | La presión sobre el PDI como captador de recursos para mantener el equipo investigador es excesiva
Condiciones laborales y de seguridad social | Creo que sería positivo la existencia de la figura del "investigador a tiempo completo"
Condiciones laborales y de seguridad social | Considero que las condiciones laborales del PDI son adecuadas
Condiciones laborales y de seguridad social | Considero que las condiciones laborales del personal investigador con cargo a proyectos son adecuadas
Condiciones laborales y de seguridad social | Me siento motivado como investigador de la UPV
Condiciones laborales y de seguridad social | La UPV dispone de un entorno de investigación adecuado para realizar mi trabajo
Condiciones laborales y de seguridad social | Existe una fragmentación en el uso de equipos que dificulta la realización de mi investigación
Condiciones laborales y de seguridad social | La asignación de personal y recursos de investigación debería contemplar criterios más allá de la carga docente
Condiciones laborales y de seguridad social | Valoraría positivamente la existencia de un "Servicio Central de Investigación" que facilitase un uso más eficiente de los equipos de la universidad
Condiciones laborales y de seguridad social | Los equipos captados en base a proyectos de investigación caen en desuso una vez terminado el proyecto por la falta de personal técnico que lo gestione
Condiciones laborales y de seguridad social | La existencia de un convenio colectivo para todos los investigadores mejoraría las condiciones laborales del personal de la UPV
Condiciones laborales y de seguridad social | Conozco la existencia de un "Plan Concilia" que facilita conciliar el desarrollo de mi actividad laboral con mi vida personal
Condiciones laborales y de seguridad social | Debería regularse el teletrabajo para facilitar la movilidad y los desplazamientos del personal investigador
Condiciones laborales y de seguridad social | La disponibilidad de recursos económicos debería ser motivación suficiente para una contratación en base a una línea de investigación
Condiciones laborales y de seguridad social | La política salarial es excesivamente rígida e imposibilita el uso de incentivos para la investigación
Condiciones laborales y de seguridad social | Las tablas salariales de la UPV están obsoletas y requieren una actualización
Condiciones laborales y de seguridad social | La coaturía en la UPV se realiza de manera adecuada
Formación y desarrollo de la carrera profesional | La formación disponible para el investigador en sus diferentes etapas es adecuada
Formación y desarrollo de la carrera profesional | Conozco la oferta formativa para investigación de la universidad
Formación y desarrollo de la carrera profesional | El acceso a la formación para investigadores de la UPV es independiente de mi situación contractual
Formación y desarrollo de la carrera profesional | La estructura de investigación a la que pertenezco organiza formación interna de interés
Formación y desarrollo de la carrera profesional | La formación recibida como investigador se reconoce de manera adecuada en mi curriculum investigador
Formación y desarrollo de la carrera profesional | Vería positiva una formación de bienvenida común a todos los investigadores que se incorporan a la UPV
Formación y desarrollo de la carrera profesional | Considero adecuado el trabajo de supervisión de tesis doctoral que se realiza en la actualidad
Formación y desarrollo de la carrera profesional | Sería positivo poner un límite al número de tesis que cada investigador puede dirigir por año
Formación y desarrollo de la carrera profesional | El investigador está saturado de numerosas tareas no relacionadas con la investigación

## Action plan
|  |  | CALENDAR | [9 empty] | Participating units (RESPONSIBLE UNIT marked yellow) | [12 empty] | Gap Principles (C&C principles following UPV application order)
|  |  | 2021 |  | 2022 |  | 2023 |  | 2024 |  | 2025 |  | Career Development Unit (UFASU) | EI (ICE) | Research Management Service (SGI) | Technology Transfer Office (I2T) | Human Resources | VINV & VIT | Vice-Rectorate for Teaching Staff and Academic Organization (VPOA) | Communications Office (ACOM) | Legal Department (Secretaría General) | Vice-Rector / Delegate Directorate for Social Dialogue, Prevention, Conciliation and Sports | Vice-Rectorate for Planning, Academic Offering and Digital Transformation | Doctorate School | Financial Management Office (Gerencia) | CG1: Ethical and Professional Aspects | [10 empty] | CG2: Recruitment and Selection | [9 empty] | CG3: Working Conditions and Social Security | [13 empty] | CG4: Training and Development
Code | Category | Action | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | [13 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | aspects/action
A1 | Ethical and Professional Aspects | Program for better dissemination, exploitation and science outreach | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 6
A1.1 |  | Prepare an online course about exploitation of research results available for the research community at UPV | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 |  | 1 |  | 1 | [5 empty] | 1
A1.2 |  | Prepare an online course about dissemination of research results | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 |  |  | 1 |  | 1 |  |  |  | 1
A1.3 |  | Create an online course about science outreach | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 |  | 1 |  | 1 |  |  |  | 1
A1.4 |  | Budgetary provisions |  | 1 | [13 empty] | 1 | [6 empty] | 1
A1.5.1 |  | Annual science fair in Valencia |  |  | 1 |  | 1 |  | 1 |  | 1 | [6 empty] | 1 |  | 1
A1.5.2 |  | Annual science fair in Gandía |  |  | 1 |  | 1 |  | 1 |  | 1 | [6 empty] | 1 |  | 1
A1.5.3 |  | Annual science fair in Alcoy |  |  | 1 |  | 1 |  | 1 |  | 1 | [6 empty] | 1 |  | 1
A1.6.1 |  | Annual inventions fair in Valencia |  |  |  | 1 |  | 1 |  | 1 |  | 1 | [5 empty] | 1 |  | 1
A1.6.2 |  | Annual inventions fair in Gandía |  |  |  | 1 |  | 1 |  | 1 |  | 1 | [5 empty] | 1 |  | 1
A1.6.3 |  | Annual inventions fair in Alcoy |  |  |  | 1 |  | 1 |  | 1 |  | 1 | [5 empty] | 1 |  | 1
A1.7 |  | Organise the annual conference on dissemination and exploitation |  |  |  | 1 |  | 1 |  | 1 |  | 1 |  |  |  | 1 |  | 1 |  | 1
A1.8.1 |  | Monitor civil society institutions interested in science outreach |  | 1 |  |  | 1 |  |  | 1 | [5 empty] | 1 |  | 1
A1.8.2 |  | Prepare agreements to be signed with civil society institutions |  |  | 1 |  |  | 1 |  |  | 1 | [9 empty] | 1
A1.9.1 |  | Agree on a new revised version of the Research Activity Index |  | 1 | 1 | 1 | [10 empty] | 1 | 1 | [6 empty] | 1
A1.9.2 |  | Approve, in the Governing Council, the new Research Activity Index |  |  |  |  | 1 | [10 empty] | 1
A1.10.1 |  | Apply for the recognition from the National Agency for Accreditation on their work on exploiting research results | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  |  |  |  | 1 |  | 1
A1.10.2 |  | Add extra points for each patent, license or research contracts |  | 1 | 1 | 1 | [11 empty] | 1
A1.11 |  | Monitor U-Ranking on the Technology Transfer field |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  |  |  | 1 |  | 1
A1.12 |  | Add extra points at the research activity index for each collection published on the open research repository, “Riunet”. |  | 1 | 1 | 1 | [11 empty] | 1
A1.13 |  | Add extra points at the research activity index for each collection published on the open research repository, “Riunet” objects flagged as “open” by the Open Access Monitor |  | 1 | 1 | 1 | [11 empty] | 1
A1.14 |  | Organise an anual UPV research awards ceremony. |  |  |  | 1 |  | 1 |  | 1 |  | 1 | [5 empty] | 1 | 1
A2 | Ethical and Professional Aspects | Observatory and learning program on legal and financial aspects for R&D activities | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | [5 empty] | 1 |  | CG1: Ethical and Professional Aspects 3: 1; CG1: Ethical and Professional Aspects 4: 1; CG1: Ethical and Professional Aspects 5: 1; CG1: Ethical and Professional Aspects 7: 1; CG3: Working Conditions and Social Security 28: 1; CG3: Working Conditions and Social Security 30: 1; CG3: Working Conditions and Social Security 31: 1; CG3: Working Conditions and Social Security 32: 1; CG3: Working Conditions and Social Security 33: 0; CG3: Working Conditions and Social Security 34: 0; CG3: Working Conditions and Social Security 35: 0; CG4: Training and Development 36: 0; CG4: Training and Development 37: 0; CG4: Training and Development 38: 1; CG4: Training and Development 39: 1; CG4: Training and Development 40: 0 | 10
A2.1.1 |  | Prepare the syllabus of the course |  | 1 |  |  | 1 | 1 |  |  |  |  | 1 | 1 | 1 | 1
A2.1.2 |  | Select the tutors and experts |  |  | 1 |  | 1 | 1 |  |  |  |  | 1 | 1 | 1
A2.1.3 |  | Prepare the online material |  |  |  | 1 | 1 | 1 |  |  |  |  | 1 | 1 | 1
A2.2.1 |  | Certificate participants | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
A2.2.2 |  | Perform a satisfaction survey among participants | [5 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 1 |  |  | 1
A2.3.1 |  | Prepare the survey |  |  | 1 | 1 | [8 empty] | 1 | 1
A2.3.3 |  | Produce a report on the needs of researchers on legal and financial aspects of R&D |  |  |  | 1 |  | 1 |  | 1 |  | 1 |  |  | 1 | 1
A3 | Ethical and Professional Aspects | Assessment and enhancement of existing R&D practices in project management, IT security and health and safety procedures | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 7
A3.1.1 |  | Select an external company for the IT assessment | 1 | [19 empty] | 1
A3.1.2 |  | Perform the IT assessment |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 | [10 empty] | 1
A3.2.1 |  | Select an external company for the Health and Safety assessment | 1 | [18 empty] | 1
A3.2.2 |  | Perform the Health and Safety assessment |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 | [9 empty] | 1
A.3.3.1 |  | Define an implementation plan | 1 | [18 empty] | 1 | 1
A.3.3.2 |  | Implement the improvement actions |  |  | 1 |  | 1 |  | 1 |  | 1 | [10 empty] | 1 | 1
A.3.3.3 |  | Assess the level of completion of the implementation plan | [6 empty] | 1 | 1 | 1 | 1 | [9 empty] | 1 | 1
A3.4.1 |  | Setup an online repository | 1 | 1 | 1 | 1 | 1 | 1 | [13 empty] | 1 | 1
A3.4.2 |  | Feed the system with best practices |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [9 empty] | 1 | 1
A3.4.3 |  | Ask users to feed the system with their own best practices |  |  | 1 |  | 1 |  | 1 |  | 1 | [10 empty] | 1 | 1
A3.4.4 |  | Verify user supplied best practices |  |  | 1 |  | 1 |  | 1 |  | 1 | [10 empty] | 1 | 1
A3.4.5 |  | Setup a search engine for best practices | [6 empty] | 1 | 1 | [11 empty] | 1 | 1
A3.4.6 |  | Make the online repository publicly available |  |  | 1 |  | 1 | 1 | [13 empty] | 1 | 1
A3.5.1 |  | Construct the syllabus of the course |  |  | 1 |  | 1 | [5 empty] | 1 | 1 |  |  | 1 |  |  |  |  | 1 |  | 1
A3.5.2 |  | Prepare materials |  |  |  | 1 |  | 1 |  |  |  |  | 1 | 1 |  |  | 1 |  |  |  |  | 1 |  | 1
A3.5.3 |  | Open the course for registration |  |  |  |  | 1 |  | 1 |  |  |  | 1 | 1 |  |  | 1 |  |  |  |  | 1 |  | 1
A3.5.4 |  | Monitor course development |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | [9 empty] | 1 |  | 1
A3.5.5 |  | Certification |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 |  |  |  |  | 1 |  | 1
A3.6.1 |  | Construct the syllabus of the IT security course offered within the scope of the initial staff training at UPV |  |  |  |  | 1 | [15 empty] | 1
A3.6.2 |  | Prepare materials | [5 empty] | 1 | 1 |  |  |  | 1 | 1 |  |  | 1 |  |  |  |  | 1 | 1
A3.6.3 |  | Include course in initial formation of staff | [7 empty] | 1 |  |  | 1 | 1 |  |  | 1 |  |  |  |  | 1 | 1
A4 | Ethical and Professional Aspects | To setup the Researcher’s Career Development Unit | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 17
A4.1.1 |  | Launch a survey on training needs |  |  | 1 | 1 | [6 empty] | 1 | 1 |  |  | 1 | [6 empty] | 1
A4.1.2 |  | Prepare a catalogue of courses |  |  |  | 1 | 1 | [5 empty] | 1 | 1 |  |  | 1 | [6 empty] | 1
A4.1.3 |  | Set up a platform with the courses |  |  |  |  | 1 | [9 empty] | 1 | [5 empty] | 1
A4.2.1 |  | Set up a platform to collect queries from researchers |  | 1 | 1 | 1 | [10 empty] | 1 | [5 empty] | 1
A4.2.2 |  | Select senior researchers in charge of the mentoring process |  |  | 1 | 1 | [10 empty] | 1 | 1
A4.3.1 |  | Hire experts for the seminars |  |  |  |  | 1 |  | 1 |  | 1 |  | 1 | 1 |  |  | 1 | [6 empty] | 1
A4.3.2 |  | Organise seminars on professional guidance for researchers | [5 empty] | 1 |  | 1 |  | 1 | 1 | 1 |  |  | 1 | [6 empty] | 1
A4.4.1 |  | Select the personnel for the new unit |  |  | 1 | 1 | [10 empty] | 1 | 1
A4.4.2 |  | Hire new personal for the unit |  |  | 1 | 1 | [10 empty] | 1 | 1
A4.4.3 |  | Design the process for service provision at the new unit |  |  | 1 | 1 | 1 | [5 empty] | 1 | 1 |  |  | 1 | 1 | [5 empty] | 1
A4.4.4 |  | Create a web portal to provide e-services related with human resources management in research, including tools like e-Recruitment |  |  |  |  | 1 | 1 | [8 empty] | 1 | [5 empty] | 1
A4.5.1 |  | Select a sample of thesis to be analysed |  |  |  |  | 1 | [9 empty] | 1 | 1
A4.5.2 |  | Audit the sample | [5 empty] | 1 | 1 | [7 empty] | 1 | 1
A4.5.3 |  | Produce a report | [7 empty] | 1 | [6 empty] | 1 | 1
A4.5.4 |  | Implement improvement actions | [8 empty] | 1 | 1 |  |  |  |  | 1 | 1
A5 | Recruitment and Selection | UPV researcher development framework | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 10
A5.1.1 |  | Select researchers from R1 to R4 from UPV as members of the group | 1 | [14 empty] | 1 | 1
A5.2.1 |  | Perform a survey to determine the most relevant information about research career development at UPV |  | 1 | 1 | 1 | [10 empty] | 1 | 1 | 1
A5.2.2 |  | Produce learning objects based on the conclusions from the survey |  |  |  | 1 | 1 | [9 empty] | 1 |  | 1
A5.2.3 |  | Publish the learning objects online | [5 empty] | 1 | [8 empty] | 1 |  | 1
A5.3.1 |  | Select key indicators about research career development based on the survey done in A5.2.1 |  |  |  | 1 | 1 | [9 empty] | 1 | 1 | 1
A5.3.2 |  | Create a dataset available online with the indicators selected | [5 empty] | 1 | [8 empty] | 1 | 1 | 1 |  |  |  | 1
A5.4 |  | Prepare the map of activities and strategies related to research career development and publish online |  |  |  | 1 | 1 | 1 | [9 empty] | 1 | 1
A5.5 |  | Setup the research career development tool | [6 empty] | 1 | 1 | [8 empty] | 1 |  | 1 |  |  |  | 1
A06 | Recruitment and Selection | Enhance recruitment practices for R2 short term research contracts |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
A6.1 |  | Analysis of the current research projects portfolio and proposal of a classification in thematic lines |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 |  | 1 | 1
A6.2.1 |  | Open a public call for a legal expert procurement |  |  | 1 | [12 empty] | 1 |  |  | 1
A6.2.2 |  | Analysis of the current legal framework |  |  | 1 | 1 | 1 | [7 empty] | 1 |  | 1 | 1 |  |  | 1
A6.2.3 |  | Proposal of a new contractual scheme | [5 empty] | 1 | 1 | [5 empty] | 1 |  | 1 | 1 |  |  | 1
A6.3 |  | Approval of the new contractual scheme | [6 empty] | 1 | [7 empty] | 1 | 1 | 1
A6.4 |  | Hiring researchers according the new contractual scheme | [7 empty] | 1 | 1 | 1 |  |  |  |  | 1
A7 | Recruitment and Selection | A one-stop shops for EU researchers merits recognition at UPV |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 12
A7.1 |  | Set up a new team to deal with EU merits recognition |  |  |  |  | 1 | 1 | [8 empty] | 1 | 1 | 1 |  | 1
A7.2 |  | Develop the web portal | [5 empty] | 1 | 1 | [7 empty] | 1 | [5 empty] | 1
A7.3 |  | Prepare 2 webinars per year about EU merits recognition |  |  |  |  | 1 |  | 1 |  |  |  | 1 | 1 |  |  | 1
A7.4 |  | Hire international researchers | [7 empty] | 1 | 1 | 1 |  |  |  |  | 1
A8 | Recruitment and Selection | Research incentives and salaries | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
A8.1 |  | Create a committee to analyse the existing remuneration scales | [6 empty] | 1 | 1 | [6 empty] | 1 | 1 | [6 empty] | 1
A8.2 |  | Make a new proposal for the remuneration scales | [7 empty] | 1 | 1 | [5 empty] | 1 | [7 empty] | 1
A8.3 |  | Prepare a new incentives system | [7 empty] | 1 | 1 | [5 empty] | 1 | [7 empty] | 1
A8.4 |  | Organise annual seminars to explain how the system works | [8 empty] | 1 | 1 | 1 | 1 |  |  | 1 | [7 empty] | 1
A9 | Working conditions and social security | Teaching and Research | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 5
A9.1 |  | Set up a committee to explore how promoting teaching among pure researchers and enabling pure researchers as principal investigator can fit in the Spanish Organic Law of Universities | 1 | [13 empty] | 1 | 1 | 1
A9.2 |  | Produce a set of recommendations to improve the situation of pure researchers at the university |  | 1 | 1 | 1 | 1 | [9 empty] | 1 | 1 | 1
A9.3 |  | Facilitate the access to learning methodologies courses for pure researchers |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1
A9.4 |  | Select a group of projects as a pilot test and extend | [5 empty] | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 1 | 1 | 1
A10 | Working conditions and social security | Definition of an action to implement and monitor the OTM-R policy at UPV |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 19
A10.1 |  | Develop an OTM-R policy in Spanish, Valencian and English | 1 | 1 |  |  | 1 | 1 | [8 empty] | 1 | 1 | 1
A10.2 |  | Develop a collection of guidelines, processes and procedures |  |  | 1 | 1 |  |  | 1 | 1 | [6 empty] | 1
A10.3 |  | Create an online course about the OTM-R |  |  | 1 |  |  |  | 1 |  |  |  | 1 | 1 |  |  | 1
A10.5 |  | Develop e-recruitment tools |  |  |  |  | 1 | 1 | [14 empty] | 1
A10.6 |  | Hire an external auditor to verify the OTM-R policy |  |  | 1 | 1 |  |  | 1 | 1 | [7 empty] | 1
A10.7 |  | Translate all research related job offers into English |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 1
A10.8 |  | Publish job posts on Euraxess |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 1
A10.9 |  | Publish a compilation of the working conditions on the recruitment portal |  |  |  |  | 1 | [9 empty] | 1 | 1
A10.10 |  | Define a job posting communication strategy |  | 1 | 1 |  | 1 | 1 | [8 empty] | 1 |  |  | 1
A10.11 |  | Analyse and improve processes for the application phase |  |  |  | 1 | 1 | 1 | [8 empty] | 1 | 1 | 1
A10.12 |  | Design a new feedback report |  |  |  |  | 1 | [9 empty] | 1
A10.13 |  | Develop a platform to file complaints online | [5 empty] | 1 | [14 empty] | 1
A11 | Training and Career Development | Tighten cooperation with EURAXESS |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [5 empty] | 1 | [47 empty] | 6 | bar: CG1: Ethical and Professional Aspects 5; CG3: Working Conditions and Social Security 22; CG3: Working Conditions and Social Security 28; CG3: Working Conditions and Social Security 30; CG4: Training and Development 38 to CG4: Training and Development 39
A11.1 |  | Inquire FECYT about the requirements for setting up an EURAXESS Contact Point at the UPV |  |  |  | 1 | [11 empty] | 1
A11.2 |  | Meet the criteria for setting up the EURAXESS Contact Point at the UPV |  |  |  |  | 1 | [10 empty] | 1
A11.3 |  | Select the first expertise area of the EURAXESS Contact Point at the UPV |  |  |  |  | 1 | [10 empty] | 1
A11.4 |  | Design the process for service provision at EURAXESS Contact Point |  |  |  |  | 1 | [10 empty] | 1
A11.5 |  | Set up a website for the EURAXESS Contact Point | [5 empty] | 1 | [9 empty] | 1 |  | 1 |  |  | 1
A11.6 |  | Set up the EURAXESS Contact Point at the UPV | [5 empty] | 1 | [9 empty] | 1
A11.7 |  | Propose adding new expertise area to the catalogue of the EURAXESS Contact Point at the UPV | [7 empty] | 1 |  | 1 | [5 empty] | 1
A11.8 |  | UPV participates in events organised by or related to EURAXESS | [5 empty] | 1 |  | 1 |  | 1 | [5 empty] | 1
A12 | Ethical and Professional Aspects | Observatory for the implementation of the Reform of reaserch assessment |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [5 empty] | 1 | [47 empty] | 7 | bar: CG1: Ethical and Professional Aspects 1 to CG1: Ethical and Professional Aspects 3; CG1: Ethical and Professional Aspects 8 to CG1: Ethical and Professional Aspects 10; CG2: Recruitment and Selection 16
A12.1 |  | Create a committee in charge of the implementation of the reform of research assessment |  |  |  |  | 1 | [7 empty] | 1 | 1 |  | 1 | 1
A12.2 |  | Participate in events related to the reform of research assessment |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 |  | 1 | 1
A12.3 |  | Prepare a study with recommendations regarding the implementation of the reform of research assessment |  |  |  |  | 1 | [7 empty] | 1 | 1 |  | 1 | 1
A12.4 |  | Prepare the plan for applying the reform of research assessment at the UPV | [5 empty] | 1 | [6 empty] | 1 | 1 |  | 1 | 1
A12.5 |  | Anual report on the state of the reform of research assesment | [5 empty] | 1 |  | 1 |  | 1 |  |  | 1 | 1 |  | 1 | 1
|  |  | 15 | 25 | 44 | 48 | 55 | 53 | 45 | 46 | 35 | 34 | 30 | 29 | 14 | 11 | 62 | 58 | 22 | 12 | 10 | 19 | 25 | 17 | 10 | 0 | 0 | 3 | 3 | 2 | 2 | 4 | 1 | 2 | 2 | 5 | 4 | 4 | 4 | 2 | 5 | 2 | 3 | 3 | 1 | 2 | 1 | 2 | 3 | 2 | 2 | 1 | 4 | 3 | 5 | 2 | 2 | 1 | 1 | 0 | 1 | 2 | 5 | 6 | 2 | 99
|  |  | 20 |  | 46 |  | 54 |  | 45.5 |  | 34.5
|  |  | YEAR1 |  | YEAR2 |  | YEAR3 |  | YEAR4 |  | YEAR5
Acronyms:
CDU: Career Development Unit - UFASU
EI: Institute for Educational Sciences - ICE
RMS: Research Management Service - SGI
TTO: Technology Transfer Office - I2T
HR: Human Resources - RH
VRITT: Vice-Rectorate for Research, Innovation and Technology Transfer - VIIT
VTAA: Vice-Rectorate for Teaching Affairs and Academics - VOAP
CO: Communications Office - ACOM
LD: Legal Department - Secretaría General
VSC: Vice-Rectorate for Sustainability and Campuses
VDR: Vice-Rectorate of Digital Resources - VRD
DS: Doctorate School
BUR: Bursar - Gerencia

## Sheet1
Status | Description (based on technical guidelines)
NEW
IN PROGRESS | Evolving as initially planned. Update the timing of achievement.
COMPLETED
EXTENDED | A new estimated deadline has to be re-set.